## Slide 1
COMMUNITY ENGAGEMENT
TRAINING OF TRAINERS MANUAL
FOR USE BY FRONT-LINE TRAINERS IN LEBANON
Implementation and Monitoring
Notes: Click to add notes

## Slide 2: Implementation
The implementation phase is a crucial step in the community engagement process, it is the interesting part of the process, where all the plans are put into action, it is basically the translation of the dreams into reality. This is usually the most time-consuming part of the process.

## Slide 3: During implementation, it is important to note :
Manging expectations, ensuring that community members and beneficiaries are well aware of what this CE project will bring to them, so that they are not disappointed by the end of the project
Adjusting activities, we learn a lot during implementation based on monitoring, feedback and learning, it is crucial to adjust plans based on learnings
Monitoring of implementation is key and is a cornerstone to the success of the project, you need to monitor activities as they happen.
At this time and before starting implementation, make sure to collect baseline data to document knowledge, attitudes and practices before and after the CE project, so you can measure progress through comparing base line and post data.
Recognize and respect diversity; and ensure that the most vulnerable are reached and engaged.

## Slide 4: Monitoring
Monitoring is measurements taken periodically during implementation—sometimes weekly, monthly or each time a community group meets.
Measurements = Monitoring Indicators

## Slide 5: Monitoring
Monitoring Indicators focuses more on the process being followed & immediate outcomes.
Evaluation Indicators focuses more on long term results, such as improvements in health.

## Slide 6: Monitoring
The number of monitoring indicators should be few & easy to collect.
With the help of the frontline worker, monitoring community-based projects is led by community members themselves.
The community group’s monitoring indicators & methods designed to monitor activities listed in the action plan.

## Slide 7: Monitoring
The link between an activity & a monitoring indicator should be clear.
Since monitoring indicators are measured easily by community members, the data should also be easy to collect, compile & use.
Monitoring is a crosscutting activity during implementation to encourage community to review and discuss monitoring results, and modify activities when needed.

## Slide 8: Types of Monitoring
There are two levels of monitoring:
  Project-level monitoring & evaluation,
  Community-led monitoring.
  This CE guide will focus on community-led monitoring because it is most relevant to your work in the field.

## Slide 9: Project-level Monitoring & Evaluation
What project managers do to track project activities & measure short term and long-term results.
They use indicators relevant to their purposes such as:
  Use of project resources,
  Adherence to time line,
  Changes in knowledge and practice of recommended behaviors,
  Changes in health.

## Slide 10: Project-level Monitoring & Evaluation
Project monitoring, mid-term and end-term evaluations are often outsourced.
Data collection methods include questionnaires, key informant interviews, clinic logs, tracking distribution and use of materials, number of people trained...etc.
Data collected are both quantitative & qualitative

## Slide 11: Community-led Monitoring
Community-led monitoring compliments project-level monitoring.
It will focus more specifically questions such as:
  “How are we doing?” (process)
  “What do we have to show for our efforts?” (immediate outcomes). This approach to monitoring is community-driven & facilitated by frontline worker. It is an essential element of engagement.

## Slide 12: Community-led Monitoring
Community-led monitoring begins with the activities listed in the Action Plan
For each planned activity, ask community groups to find to the question: “What outcomes are we (community members) expecting?”
Brainstorm community members to formulate indicators from these outcomes.

## Slide 13: Community-led Monitoring
Make sure that expected outcomes are observable results of activities.
Community ability to monitor exposure to information, changing attitudes & raising awareness are difficult. So, should not be addressed in a community action plan.

## Slide 14: Community-led Monitoring
Community will be able to monitor infrastructure problems, service quality, income generation, improving the local environment, waste disposal. So, it should be listed in the Action Plan.
Example of process indicators.
  Accessing resources,
  Extra meetings,
  Volunteers selected, action from a partner, etc.

## Slide 15: WHAT ARE THE ESSENTIAL INDICATORS FOR Community ACTIVITIES?
ESSENTIAL
INTERESTING
Nice to Know
MONITORING
Information from the indicator help us modify our activity (ESSENTIAL)
Information from the indicator is not directly linked to modifying the activity (Interesting or Nice to Know). DROP IT

## Slide 16: Coordinating Monitoring With Implementation:
When and how frequently to monitor depends on the activity.
  If the plan to implement activity in the school: Coordinate with the school
    Possible indicator: photograph finished posters both in the school & where they are displayed around the community
  If the plan to implement activity in the health clinic OR paying a water bill:
  Coordinate with local health services
    Clinic records OR water establishment.

## Slide 17: Coordinating Monitoring With Implementation
What to do with monitoring results?
  Work with your community focal points to display and explain the monitoring results so group members can easily see progress and outcomes.
  Use graphs and tables, clinic records, photographs, samples of products, testimonials...etc.
  Prepare group members that some monitoring results will be disappointing.

## Slide 18: Coordinating Monitoring With Implementation
What to do with monitoring results?
  Explain that these results suggest that there are problems in implementation and should not be ignored.
  Facilitate an open discussion to find solutions and agree on actions to improve performance.
  Focus on moving forward, not looking back to blame poor performers.
  Time at the meeting should also be taken to celebrate successes as they occur along the way.

## Slide 19: Coordinating Monitoring With Implementation
OBSERVATION RESULTS
Negative Results
Positive Results
Share results
with relevant
contacts
Ask for support
from your
organization
Revisit CE Steps 3 & 4

## Slide 20: Dissemination Monitoring Information
Dissemination of Monitoring information
Upward to project managers
To other community groups and implementing partners
Through social media and community gatherings.
Horizontally
Through reports and meetings

## Slide 21: Facilitating Community-led Monitoring
Help community groups to identify concrete indicators to monitor during action planning meeting.
Lead a discussion to develop monitoring indicators for each activity by asking these questions:
  How can we see that the activity is happening (that steps are being taken)? These are process indicators.
  What is the result of the activity? These are outcome indicators.

## Slide 22: Facilitating Community-led Monitoring
Decide how the indicators will be observed.
Train selected community members in how to collect monitoring information.
Provide materials for monitoring
Make a monitoring schedule—when should monitors collect information and return it to you or the focal point?

## Slide 23: Facilitating Community-led Monitoring
Work with community members to compile the monitoring information to facilitate understanding
Lead a discussion about what message comes from this information:
  “How are we doing?”
  “What can we change to improve results?”
Show how to use the information from monitoring to improve implementation.

## Slide 24: Facilitating Community-led Monitoring
Return to the Action Plan to add changes to implementation, who will be responsible &and when.
You and/or the focal point should share monitoring information:
  Upward to project managers through reports and meetings.
  Horizontally to the other community groups through social media & community gatherings.

## Slide 25: Methods for collecting M & E Information
Types of Research in Communication Programmes
Types of Research | Broad Purposes of | Main Questions Answered
Formative research (situation analysis, Baseline measurement) | Examines current situation, develops objectives and baselines for subsequent measurement, and determines key concepts | Where are we now? Is strategic communication needed? Who needs it, why, how, when, and where?
Assessing immediate reactions (pre-testing) | Identifies essential design features | Will this work? How should strategic communication best be carried out?

## Slide 26: Methods for collecting M & E Information
Types of Research in Communication Programmes
Types of Research | Broad Purposes of | Main Questions Answered
Monitoring processes and early changes | Monitors inputs and outputs; assesses reach, quality, participant satisfaction, and early indications of behavioral, organizational and social change | How are we doing? To what extent are planned activities actually realized? How well is the information provided and dialogue supported? What early signs of progress can we detect?
Evaluating outcomes and impacts | Measures behavioral, organizational and social change results and determines contribution of strategic communication to these results | How did we do? What outcomes are observed? What do the outcomes mean? What difference did strategic communication make?

## Slide 27: Distinction between Qualitative and Quantitative Research
QUALITATIVE RESEARCH | QUANTITATIVE RESEARCH
Provides depth of understanding Asks “why?” Studies motivation Is subjective Enables discovery Is exploratory Allows insights into behaviors, trends, etc. Interprets Relies on small, purposeful sampling Does not allows generalizations Focuses on processes Allows for interaction between facilitator and participants | Measures level of occurrence Asks “how many?”, “How often?” Studies action Is objective Provides proofs Is definitive Measures level of actions, trends, etc. Describes Relies on statistical, large random sampling Allows for broad generalizations of finding to larger populations Focuses on outcomes Facilitates the use of statistics for aggregating, summarizing, describing, and comparing data.